## TODO Before 0.0.1
Nr | TODO | status | Done at | Details
1 | create character movement, jumping, dodging | done | 2024-05-11
2 | add shooting possibility | done | 2024-05-15
3 | create simple target (enemy) | done | 2024-05-17
4 | try to shoot in enemy and walls | done | 2024-05-17
5 | improve enemy chasing the player with some pathfinding system | done | 2024-05-18
6 | enrich enemies and character with basic HP, MP AND STAMINA | done | 2024-06-23
7 | achieve enemies AI movement and trying to attack character | done | 2024-05-19
8 | enemies AI - trying to avoid collision with projectiles | done | 2024-05-19
9 | add first simple light-impulse shot attack with mp usage and some cast time | done | 2024-06-23
10 | create enemy mp, hp, xp system AND STAMINA | done | 2024-06-30 | (if enemy shoot player or hit / kill successfully - he gain exp (next generated enemies of this type and current 1 enemy will be harder + hp, + speed, + dmg)
11 | enemies drop souls on dead | done | 2024-06-25
12 | add enemy hp bar and ? Mp | done | 2024-06-30
13 | enemies reduce player hp | done | 2024-06-12 | enemies attacks use their mp, so with time attacks become more rair.
14 | player attacks reduce enemy hp (hp shown) | done | 2024-06-30
15 | add multilang | done | 2024-06-13
16 | add enemy exp system | done | 2024-06-30 | when enemy does damage to player - it gain exp to enemy exp (all next enemies will be harder and harder)
17 | add player exp system |  | 2024-06-30 | skills gain exp not player
20 | polish basic enemy to be able to reuse some components in other enemies | done | 2024-07-02
27 | enemy spawner in some rooms | done | 2024-07-02 | close the door - need to kill him - he is static, and spawn enemies
18 | add vignette - for fast movement, low hp | done | 2024-07-02
19 | add UI - please check ui prototype file in assets/2d | done | 2024-09-27
21 | polish player components - clean up before v 0.0.1 | done | 2024-08-16
22 | add fireplace of fontain on map -where player can spend souls for mp or hp regen | done | 2024-09-06
23 | add shop between stages where player can improve or buy new skills | todo
24 | add second stage same but harder | todo
25 | translate all content before release of demo! | todo |  | UA, ENG, LT
26 | player has N lifes for stage | done | 2024-09-06 | after then droped back to shop or to begin of game(depends on stage)
27 | on each death -player loose half souls | done | 2024-09-06
28 | after last life lost - all souls lost, and materials - only gold coins left | todo
29 | add first stage of game with some aim (requirements in other TODO's)( list below) | in-progress
30 | change cursor while casting some skill to some symbols (ua, lt)? | todo
31 | add pickaxe, or skill destructing some blocks | todo
32 | add destructive blocks in some room outs | todo
33 | add collectable gems | todo
34 | gems used to activate laser from fontain to door | todo
35 | add gold coins | todo |  | used to upgrade character start stats and refil consumable things
36 | gold coins could be used to buy the consumable items and upgrade player | todo
37 | add consumable tablets (read and drop + consume some souls on usage) | in-progress | 2024-09-27
38 | destructive blocks drop stones (even doors) | todo
39 | using stones you can build the stairs to fontains, and final stairs to next stage | todo
40 | add path controll - to open the gate on second shop/stage | todo |  | ( need to build stairs to next floor)
41 | add new enemies (rats or small bugs) - who will spawn all the time | todo |  | destroy door, build stairs
42 | add logic that on deadend room spawns the gold, gems and stone | todo |  | dead end rooms will contain necessary resources for finishing the stage (gems, gold, stone)
43 | add logic that only after such deadend room will be next fontain and door | todo |  | to be sure - player collect enough gems or can collect to break the door
44 | add enemies movement model when they detect player | done | 2024-09-10 | move readial around player and try to attack spontaniously

## TODO's
Nr | TODO | status | Done at | Details
1 | skills add fireball | todo |  | more mana usage, explode on damage, longer cast time)
2 | skills add froze ray | todo |  | low constant damage while handle skill (low but constant mana usage, good agains hordes in line)
3 | skills add active jump/tp | todo |  | or etc for faster movement
4 | skills add very fast cast field which push all out from player with long cd | todo |  | low cast time, low damage, strong push, long cd
5 | add random procedure generated dungeons | done | 2024-09-01 | 1 - Entrance on stage and exit, related located at first block and last; 2 - Columns in each block - 1 - 4 random 3 - Brick/broken structures located on map (0-5) random 4 - Stage has random form depends on number of blocks (letter L, P, I etc) 5 - Light - under top and on walls each N meters torch 6 - Bonus healer potions or armor - located on map. 7 - ? Traps - floor zones where something can fall on head or etc
6 | add player creation screen | todo
7 | add player saving | todo
8 | add menu | todo
9 | add sounds | todo
10 | final - concept in the phone notes (roof and cubes) | todo
11 | Columns randomnless | todo |  | should be different and sometimes not collumns but some strange objects
12 | wall color - new levels or rooms should looks different little bit | todo
13 | in wall could be traps | todo |  | when player commes to close to wall - wall openes and some enemy shoot player

## Logs
Date | What was done :D
2024-05-04 | initial commit, with adding basic mesh model from blender and camera
2024-05-08 | replace mesh with free one from Kenney assets, improve movement and test some animations
2024-05-10 | create dev log file (as I forget to do it when start project), and describe basic todo list, add first static/autorun nodes to handle events, configurations and player parameters
2024-05-11 | fix moving, add shift moving, and shift jump, add camera collision with terrain, build simple training map, add simple shooting prototype ( shooting from rod controlled in 2 different modes)
2024-05-12 | rework shooting, fix camera, lot of work to adjust shooting from camera view to cursor on screen, add zoom on right button, found bug - need to rework projectiles as in high speeds - it not collide with meshes
2024-05-15 | but projectiles in high speed collide with character3d and that's enough for me, added enemy for tests, firsts steps to implement enemy agrs on player moves in his detection area
2024-05-17 | finally enemy rotates and moves in player side.
2024-05-18 | add custom simple AI for enemies - they can idle move around, and start to chasing player if he is in agr bound
2024-05-19 | enemies trying to avoid shots and aggr in player direction even if player is too far, add temp enemy spawner and use dead animation,add enemies when reach the player start to attack player, player camera shakes on attack
2024-05-28 | apply addon with prototype textures for testmap, add new TODO's + ui prototype
2024-05-29 | migrate logs to xls, add upgrade todo's, add spagetti health_component - same for enemy and player, enemy can be damaged by amount of projectile
2024-06-02 | work on particles for projectiles - looks good but need finilize for simple attack
2024-06-08 | work on partickles, explosion particles, animation of damage for player and enemies, add lighthing, shaders and fog
2024-06-09 | start work on damage flash component
2024-06-12 | Implement damage flash component - for enemies and player, improve it. BIG DAY, finally undestand why shooting was bad near walls (cause I calculate direction from weapon to mouse( and they was in one flat axis)), try on first translation staff, start refactoring skills for player - create firs resources
2024-06-13 | add some translation and test it using spark skill resource, add controller system for skill usage by player based on skill_resource + skill_controller + player_skill_controller, with calls using abstact level. Player will be able first to choose which skill he want to use.
2024-06-15 | add abstraction for mana component and etc. found issue that controllets not use the timers of parent
2024-06-16 | Fix issue - not enough to extend script in code, the child component must inherit from parent scene all timers and etc. Implement primitive mana regen
2024-06-17 | Add stamina component, fix inheritence for health and mana components
2024-06-19 | move player skills to controllers (including jump, run, aim etc.)
2024-06-20 | refactor again - basic stamina and jump controllers used from userSkillController now, fix bugs when skill consume stamina continuasly, add lock system for mana and stamina skills - to avoid paralel skill usages
2024-06-22 | work on glow effect (looks nice), fix lags when full screeen - resolution wsa to high - found place where it can be changed, healing animation
2024-06-24 | add souls, souls drop and collecting. Lot of fun, but source consumable… Now enemy on death drop souls, and player can collect them. Add collecting fade out and counting.
2024-06-25 | refactor enemy, not best but moved almost all to dodge, idle, etc components/controllers
2024-06-30 | finish refactoring enemy, fix bug when player shoot underground while camera close to wall, add stat bars for enemies
2024-07-02 | finish with mp bar, remove shadows from particles, adjust bars, found prop to glow (hdr2d in subView) - looks ugly), add enemy-spawner for enemies, add vignete on damage, run aim effects
2024-07-03 | fix bug with camera jumps when sprint and aim, fix bug no damage when on head of enemy, add push effect and skill
2024-07-06 | oh…a lot of work with light, meshes gridmap, etc., no results only pain and not bad looking some kind of map
2024-07-07 | gridMap removed - shitty staff. Work on random procedure generation of map. Have large progress with common Node3D and script for spawn tiles. Tiles could be spawn as rooms of different sizes, I can spawn long tunels of tiles with almost no collisions(low possibility). Next step apply rooms to tunels and add walls + roof
2024-07-08 | add generation of exit in random side /random place
2024-07-10 | fix existing generation of exit. Improve to reduce complexity, first attempts to add additional room
2024-07-12 | DONE random floor and exist generated perfectly! Next step to clean up that generator class and add the walls
2024-07-19 | Added system of room saving - and now each generated room save some info. Next step to use it while walls generation - to catch where wall should be and where not.
2024-07-20 | Add deadend rooms and modify the common room schema, first attemts to add a walls - not bad -but lot of work in future
2024-07-21 | Finish walls adding stuff. It works good. Start refactoring the mapGenerator class - extract WallBuilder and SurfaceBuilder
2024-07-22 | Fixed the issue when camere went inside the walls - so it was my fail, cause camera shouldn’t be so far from player - if It's - then needed additional configs to handle collisions or etc. cause scene center then can be out of map
2024-07-22 | Refactored tunel generation. Add some ceil generation.
2024-07-29 | add different heigh room generation, fix floor transparency
2024-08-06 | create a torch and candle - add optimisation for shading, add fog effect
2024-08-08 | work with textures, create new simple meshes in godot for walls, corridors, columns. Debug lights and shadows.
2024-08-28 | add enemies agr each other and fix agr of enemies, looks good
2024-09-04 | add mass spawn of enemies on attack or agr zone enter, add primitive player respawn zone and dead souls drop and life minus
2024-09-05 | add gui theme, add custom gui bars, connect them to player, fix spawner
2024-09-08 | learn lowpoly modeling in blender
2024-09-09 | add tasks aim of game and replayability, non sleep night gave lot of ideas, hope I will implement them, check additionaly details tab
2024-09-10 | add enemies move randompy circles - looks fine, PI/2 is 90 - it consume one day to debug -_-
2024-09-13 | add belt, inventory, hands views (will change pc - could be long itteruption)
2024-09-20 | add first item to the inventory screen
2024-09-21 | add resizability for the belt, inventory and etc, add button to open/close inventory
2024-09-24 | add drag and drop first steps to belt, need to add this for inventory/hands and remove object in old place
2024-09-27 | work on drag and drop
2024-09-28 | work on drag and drop ( I hate this)
2024-09-29 | finally, drag and drop works as I want. Items can be merged or change one anothers place. Player cant drop item or split
2024-09-30 | items connected to skills, when Item taken to hand - skill can be used!, clean up 50+ warnings
2024-10-01 | items can be droped and collected to invenory!

## Details
gameplay
on menu, before game:
before start game player can shop some self upgrades (permanent), and some consumable tablets (hp, mp, stamina, speed up etc.)
this updates can be both by only curency which not disapear after death of player - gold, as gold used to be burried with the heroes and etc
game:
starts on first room on the fontain, need to reach last room of stage and build stairs to next stage
kill enemies gives the souls - main curency during the run, can be spend when use consumable items and to shop between stages - new weapons and consumables
stage contain doors which could be oppened using fontain power, to use it player need - collect stones to build stairs to fontain, harwest gems - and put the gems to the fontain fireplace, it will produce shot in the door and door will opened
stone, gems and gold could be spawned in common rooms in very low quantities, and in bigger in deadend rooms where will be more enemies
game stage will take 1-n doors to open and after last door - need to build the stairs to next floor
shop:
trader stage - guy who will take souls and will sell you improvements for existing spells or new spells
game process:
clean up stage, shop, and clean up next stage with harder monsters - as they will be harder after each kick player, or dying.
player can die N times and he will throwed back to last fontain, after lives ended - die permanently
game could be saved only between stages in the shop
player don’t have own expirience, but have skill expirience system , which will be also saved permanently between stages - so person who bouth n times same weapon and use it - will be more skilled with it
game final is to reach ,for instance 5-th floor, after what player can choose to finish story - small text story about that player what happened with player
or player can choose to go to endless mode and try to reach as high as possible, score system to compete between players

## insane calcs
max_lvl | enemy lvl | max exp
10 | 0 | 10
| 1 | 30
| 2 | 60
| 3 | 100
| 4 | 150
| 5 | 210
| 6 | 280
| 7 | 360
| 8 | 450
| 9 | 550
| 10 | 660