## TODO Before 0.0.1
Nr | TODO | status | Done at | Details
1 | create character movement, jumping, dodging | done | 2024-05-11
2 | add shooting possibility | done | 2024-05-15
3 | create simple target (enemy) | done | 2024-05-17
4 | try to shoot in enemy and walls | done | 2024-05-17
5 | improve enemy chasing the player with some pathfinding system | done | 2024-05-18
6 | enrich enemies and character with basic HP, MP AND STAMINA | in-progress
7 | achieve enemies AI movement and trying to attack character | done | 2024-05-19
8 | enemies AI - trying to avoid collision with projectiles | done | 2024-05-19
9 | add first stage of game with some aim (requirements in other TODO's) | todo
10 | add first simple light-impulse shot attack with mp usage and some cast time | in-progress
11 | create enemy mp, hp, xp system AND STAMINA | in-progress |  | (if enemy shoot player or hit / kill successfully - he gain exp (next generated enemies of this type and current 1 enemy will be harder + hp, + speed, + dmg)
12 | enemies drop souls on dead | todo
13 | player has N lifes for stage | in-progress |  | after then droped back to shop or to begin of game(depends on stage)
14 | on each death -player loose half souls | todo
15 | add enemy hp bar and ? Mp | todo
16 | enemies reduce player hp | done | 2024-06-12 | enemies attacks use their mp, so with time attacks become more rair.
17 | player and ? trap attacks reduce enemy hp (hp shown) | todo
18 | add vignette - for fast movement, low hp | todo
19 | add UI - please check ui prototype file in assets/2d | todo
20 | polish basic enemy to be able to reuse some components in other enemies | todo
21 | polish player components - clean up before v 0.0.1 | todo
22 | add fireplace of fontain on map -where player can spend souls for mp or hp regen | todo
23 | add shop between stages where player can improve or buy new skills | todo
24 | add second stage same but harder | todo
25 | add path controll - to open the gate on second shop/stage | todo |  | need to have N energy and souls to open door
26 | add multilang | done | 2024-06-13
27 | translate all content before release of demo! | todo |  | UA, ENG, LT

## TODO's
Nr | TODO | status | Done at | Details
1 | skills add fireball | todo |  | more mana usage, explode on damage, longer cast time)
2 | skills add froze ray | todo |  | low constant damage while handle skill (low but constant mana usage, good agains hordes in line)
3 | skills add active jump/tp | todo |  | or etc for faster movement
4 | skills add very fast cast field which push all out from player with long cd | todo |  | low cast time, low damage, strong push, long cd
5 | add random procedure generated dungeons | todo |  | 1 - Entrance on stage and exit, related located at first block and last; 2 - Columns in each block - 1 - 4 random 3 - Brick/broken structures located on map (0-5) random 4 - Stage has random form depends on number of blocks (letter L, P, I etc) 5 - Light - under top and on walls each N meters torch 6 - Bonus healer potions or armor - located on map. 7 - ? Traps - floor zones where something can fall on head or etc
6 | add player creation screen | todo
7 | add player saving | todo
8 | add menu | todo
9 | add sounds | todo

## Logs
Date | What was done :D
2024-05-04 | initial commit, with adding basic mesh model from blender and camera
2024-05-05
2024-05-06
2024-05-07
2024-05-08 | replace mesh with free one from Kenney assets, improve movement and test some animations
2024-05-09
2024-05-10 | create dev log file (as I forget to do it when start project), and describe basic todo list, add first static/autorun nodes to handle events, configurations and player parameters
2024-05-11 | fix moving, add shift moving, and shift jump, add camera collision with terrain, build simple training map, add simple shooting prototype ( shooting from rod controlled in 2 different modes)
2024-05-12 | rework shooting, fix camera, lot of work to adjust shooting from camera view to cursor on screen, add zoom on right button, found bug - need to rework projectiles as in high speeds - it not collide with meshes
2024-05-13
2024-05-14
2024-05-15 | but projectiles in high speed collide with character3d and that's enough for me, added enemy for tests, firsts steps to implement enemy agrs on player moves in his detection area
2024-05-16
2024-05-17 | finally enemy rotates and moves in player side.
2024-05-18 | add custom simple AI for enemies - they can idle move around, and start to chasing player if he is in agr bound
2024-05-19 | enemies trying to avoid shots and aggr in player direction even if player is too far, add temp enemy spawner and use dead animation,add enemies when reach the player start to attack player, player camera shakes on attack
2024-05-20
2024-05-21
2024-05-22
2024-05-23
2024-05-24
2024-05-25
2024-05-26
2024-05-27
2024-05-28 | apply addon with prototype textures for testmap, add new TODO's + ui prototype
2024-05-29 | migrate logs to xls, add upgrade todo's, add spagetti health_component - same for enemy and player, enemy can be damaged by amount of projectile
2024-06-02 | work on particles for projectiles - looks good but need finilize for simple attack
2024-06-08 | work on partickles, explosion particles, animation of damage for player and enemies, add lighthing, shaders and fog
2024-06-09 | start work on damage flash component
2024-06-12 | Implement damage flash component - for enemies and player, improve it. BIG DAY, finally undestand why shooting was bad near walls (cause I calculate direction from weapon to mouse( and they was in one flat axis)), try on first translation staff, start refactoring skills for player - create firs resources
2024-06-13 | add some translation and test it using spark skill resource, add controller system for skill usage by player based on skill_resource + skill_controller + player_skill_controller, with calls using abstact level. Player will be able first to choose which skill he want to use.
2024-06-15 | add abstraction for mana component and etc. found issue that controllets not use the timers of parent
2024-06-16 | Fix issue - not enough to extend script in code, the child component must inherit from parent scene all timers and etc. Implement primitive mana regen
2024-06-17 | Add stamina component, fix inheritence for health and mana components
2024-06-19 | move player skills to controllers (including jump, run, aim etc.)
2024-06-20 | refactor again - basic stamina and jump controllers used from userSkillController now, fix bugs when skill consume stamina continuasly, add lock system for mana and stamina skills - to avoid paralel skill usages