## TODO Before 0.0.1
Nr | TODO | status | Done at | Details
1 | create character movement, jumping, dodging | done | 2024-05-11
2 | add shooting possibility | done | 2024-05-15
3 | create simple target (enemy) | done | 2024-05-17
4 | try to shoot in enemy and walls | done | 2024-05-17
5 | improve enemy chasing the player with some pathfinding system | done | 2024-05-18
6 | enrich enemies and character with basic HP, MP AND STAMINA | done | 2024-06-23
7 | achieve enemies AI movement and trying to attack character | done | 2024-05-19
8 | enemies AI - trying to avoid collision with projectiles | done | 2024-05-19
9 | add first simple light-impulse shot attack with mp usage and some cast time | done | 2024-06-23
10 | create enemy mp, hp, xp system AND STAMINA | done | 2024-06-30 | (if enemy shoot player or hit / kill successfully - he gain exp (next generated enemies of this type and current 1 enemy will be harder + hp, + speed, + dmg)
11 | enemies drop souls on dead | done | 2024-06-25
12 | add enemy hp bar and ? Mp | done | 2024-06-30
13 | enemies reduce player hp | done | 2024-06-12 | enemies attacks use their mp, so with time attacks become more rair.
14 | player attacks reduce enemy hp (hp shown) | done | 2024-06-30
15 | add multilang | done | 2024-06-13
16 | add enemy exp system | done | 2024-06-30 | when enemy does damage to player - it gain exp to enemy exp (all next enemies will be harder and harder)
17 | add player exp system |  | 2024-06-30 | skills gain exp not player
20 | polish basic enemy to be able to reuse some components in other enemies | done | 2024-07-02
27 | enemy spawner in some rooms | done | 2024-07-02 | close the door - need to kill him - he is static, and spawn enemies
18 | add vignette - for fast movement, low hp | done | 2024-07-02
19 | add UI - please check ui prototype file in assets/2d | in-progress
21 | polish player components - clean up before v 0.0.1 | todo
22 | add fireplace of fontain on map -where player can spend souls for mp or hp regen | todo
23 | add shop between stages where player can improve or buy new skills | todo
24 | add second stage same but harder | todo
25 | add path controll - to open the gate on second shop/stage | todo |  | need to have N energy and souls to open door
26 | translate all content before release of demo! | todo |  | UA, ENG, LT
28 | add first stage of game with some aim (requirements in other TODO's) | todo
29 | player has N lifes for stage | todo |  | after then droped back to shop or to begin of game(depends on stage)
28 | on each death -player loose half souls | todo
change cursor while casting some skill to some symbols (ua, lt)?

## TODO's
Nr | TODO | status | Done at | Details
1 | skills add fireball | todo |  | more mana usage, explode on damage, longer cast time)
2 | skills add froze ray | todo |  | low constant damage while handle skill (low but constant mana usage, good agains hordes in line)
3 | skills add active jump/tp | todo |  | or etc for faster movement
4 | skills add very fast cast field which push all out from player with long cd | todo |  | low cast time, low damage, strong push, long cd
5 | add random procedure generated dungeons | in-progress |  | 1 - Entrance on stage and exit, related located at first block and last; 2 - Columns in each block - 1 - 4 random 3 - Brick/broken structures located on map (0-5) random 4 - Stage has random form depends on number of blocks (letter L, P, I etc) 5 - Light - under top and on walls each N meters torch 6 - Bonus healer potions or armor - located on map. 7 - ? Traps - floor zones where something can fall on head or etc
6 | add player creation screen | todo
7 | add player saving | todo
8 | add menu | todo
9 | add sounds | todo

## Logs
Date | What was done :D
2024-05-04 | initial commit, with adding basic mesh model from blender and camera
2024-05-05
2024-05-06
2024-05-07
2024-05-08 | replace mesh with free one from Kenney assets, improve movement and test some animations
2024-05-09
2024-05-10 | create dev log file (as I forget to do it when start project), and describe basic todo list, add first static/autorun nodes to handle events, configurations and player parameters
2024-05-11 | fix moving, add shift moving, and shift jump, add camera collision with terrain, build simple training map, add simple shooting prototype ( shooting from rod controlled in 2 different modes)
2024-05-12 | rework shooting, fix camera, lot of work to adjust shooting from camera view to cursor on screen, add zoom on right button, found bug - need to rework projectiles as in high speeds - it not collide with meshes
2024-05-13
2024-05-14
2024-05-15 | but projectiles in high speed collide with character3d and that's enough for me, added enemy for tests, firsts steps to implement enemy agrs on player moves in his detection area
2024-05-16
2024-05-17 | finally enemy rotates and moves in player side.
2024-05-18 | add custom simple AI for enemies - they can idle move around, and start to chasing player if he is in agr bound
2024-05-19 | enemies trying to avoid shots and aggr in player direction even if player is too far, add temp enemy spawner and use dead animation,add enemies when reach the player start to attack player, player camera shakes on attack
2024-05-20
2024-05-21
2024-05-22
2024-05-23
2024-05-24
2024-05-25
2024-05-26
2024-05-27
2024-05-28 | apply addon with prototype textures for testmap, add new TODO's + ui prototype
2024-05-29 | migrate logs to xls, add upgrade todo's, add spagetti health_component - same for enemy and player, enemy can be damaged by amount of projectile
2024-06-02 | work on particles for projectiles - looks good but need finilize for simple attack
2024-06-08 | work on partickles, explosion particles, animation of damage for player and enemies, add lighthing, shaders and fog
2024-06-09 | start work on damage flash component
2024-06-12 | Implement damage flash component - for enemies and player, improve it. BIG DAY, finally undestand why shooting was bad near walls (cause I calculate direction from weapon to mouse( and they was in one flat axis)), try on first translation staff, start refactoring skills for player - create firs resources
2024-06-13 | add some translation and test it using spark skill resource, add controller system for skill usage by player based on skill_resource + skill_controller + player_skill_controller, with calls using abstact level. Player will be able first to choose which skill he want to use.
2024-06-15 | add abstraction for mana component and etc. found issue that controllets not use the timers of parent
2024-06-16 | Fix issue - not enough to extend script in code, the child component must inherit from parent scene all timers and etc. Implement primitive mana regen
2024-06-17 | Add stamina component, fix inheritence for health and mana components
2024-06-19 | move player skills to controllers (including jump, run, aim etc.)
2024-06-20 | refactor again - basic stamina and jump controllers used from userSkillController now, fix bugs when skill consume stamina continuasly, add lock system for mana and stamina skills - to avoid paralel skill usages
2024-06-22 | work on glow effect (looks nice), fix lags when full screeen - resolution wsa to high - found place where it can be changed, healing animation
2024-06-24 | add souls, souls drop and collecting. Lot of fun, but source consumable… Now enemy on death drop souls, and player can collect them. Add collecting fade out and counting.
2024-06-25 | refactor enemy, not best but moved almost all to dodge, idle, etc components/controllers
2024-06-30 | finish refactoring enemy, fix bug when player shoot underground while camera close to wall, add stat bars for enemies
2024-07-02 | finish with mp bar, remove shadows from particles, adjust bars, found prop to glow (hdr2d in subView) - looks ugly), add enemy-spawner for enemies, add vignete on damage, run aim effects
2024-07-03 | fix bug with camera jumps when sprint and aim, fix bug no damage when on head of enemy, add push effect and skill
2024-07-06 | oh…a lot of work with light, meshes gridmap, etc., no results only pain and not bad looking some kind of map
2024-07-07 | gridMap removed - shitty staff. Work on random procedure generation of map. Have large progress with common Node3D and script for spawn tiles. Tiles could be spawn as rooms of different sizes, I can spawn long tunels of tiles with almost no collisions(low possibility). Next step apply rooms to tunels and add walls + roof
2024-07-08 | add generation of exit in random side /random place
2024-07-10 | fix existing generation of exit. Improve to reduce complexity, first attempts to add additional room
2024-07-12 | DONE random floor and exist generated perfectly! Next step to clean up that generator class and add the walls
2024-07-19 | Added system of room saving - and now each generated room save some info. Next step to use it while walls generation - to catch where wall should be and where not.
2024-07-20 | Add deadend rooms and modify the common room schema, first attemts to add a walls - not bad -but lot of work in future
2024-07-21 | Finish walls adding stuff. It works good. Start refactoring the mapGenerator class - extract WallBuilder and SurfaceBuilder
2024-07-22 | Fixed the issue when camere went inside the walls - so it was my fail, cause camera shouldn’t be so far from player - if It's - then needed additional configs to handle collisions or etc. cause scene center then can be out of map

## insane calcs
max_lvl | enemy lvl | max exp
10 | 0 | 10
| 1 | 30
| 2 | 60
| 3 | 100
| 4 | 150
| 5 | 210
| 6 | 280
| 7 | 360
| 8 | 450
| 9 | 550
| 10 | 660